Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 29 September 2026 |
| --- | --- |
| Team ID | SWTID-2026-3192 |
| Project Name | AI WeatherWise |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup | USN-1 | As a developer, I can set up the Node.js/Express server with a MongoDB (Mongoose) connection so the API can start. | 3 | High | S. Santhiya |
| Sprint-1 |  | USN-2 | As a developer, I can configure the project structure, environment variables, and a centralized error handler with a 404 handler. | 3 | High | Parameshwari |
| Sprint-1 | Registration | USN-3 | As a user, I can register with my name, email, and password (stored hashed) and receive a JWT. | 5 | High | Rajalakshmi |
| Sprint-1 |  | USN-4 | As a user, I get a clear error if I register with an existing email or invalid details. | 2 | Medium | Rajalakshmi |
| Sprint-1 | Login | USN-5 | As a user, I can log in with my email and password and receive a JWT. | 5 | High | Zeba Fathima |
| Sprint-1 |  | USN-6 | As a user, my JWT is verified by the auth middleware so only I can access protected routes. | 2 | High | S. Santhiya |
| Sprint-2 | Weather Lookup | USN-7 | As a developer, I can integrate the OpenWeatherMap API through a weather service. | 5 | High | Parameshwari |
| Sprint-2 |  | USN-8 | As a user, I can view current weather conditions for any city (GET /api/weather/:city). | 5 | High | S. Santhiya |
| Sprint-2 |  | USN-9 | As a user, I get a meaningful error when a city is invalid or the weather service fails. | 3 | Medium | Zeba Fathima |
| Sprint-2 | Saved Locations | USN-10 | As a user, I can save a location with its name and coordinates. | 4 | High | Rajalakshmi |
| Sprint-2 |  | USN-11 | As a user, I can view, update, and delete my saved locations. | 3 | Medium | Rajalakshmi |
| Sprint-3 | AI Recommendations | USN-12 | As a developer, I can integrate Google Gemini AI through an AI service. | 5 | High | S. Santhiya |
| Sprint-3 |  | USN-13 | As a user, I can get an AI-generated weather summary and recommendation (POST /api/ai/weather-recommendation). | 5 | High | Parameshwari |
| Sprint-3 |  | USN-14 | As a user, my input to the AI route is validated so incomplete requests are rejected. | 2 | Medium | Zeba Fathima |
| Sprint-3 | Saved Locations | USN-15 | As a user, I can mark a saved location as a favorite for quick lookup. | 3 | Medium | Rajalakshmi |
| Sprint-3 | Data Storage | USN-16 | As a developer, I can store weather readings and AI insights in MongoDB linked to locations. | 5 | Medium | Parameshwari |
| Sprint-4 | Testing | USN-17 | As a tester, I can verify every endpoint in Postman with positive and negative cases. | 5 | High | Zeba Fathima |
| Sprint-4 |  | USN-18 | As a tester, I can run User Acceptance Testing and log any bugs found. | 3 | High | S. Santhiya |
| Sprint-4 |  | USN-19 | As a developer, I can fix reported bugs and refine error responses. | 4 | Medium | Rajalakshmi |
| Sprint-4 | Documentation | USN-20 | As a team, we can prepare the technical documentation with architecture and ER diagrams. | 5 | Medium | Parameshwari |
| Sprint-4 |  | USN-21 | As a team, we can record the project demo and API testing videos. | 3 | Low | Zeba Fathima |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 24 Aug 2026 | 29 Aug 2026 | 20 | 29 Aug 2026 |
| Sprint-2 | 20 | 6 Days | 31 Aug 2026 | 05 Sep 2026 | 20 | 05 Sep 2026 |
| Sprint-3 | 20 | 6 Days | 07 Sep 2026 | 12 Sep 2026 | 20 | 12 Sep 2026 |
| Sprint-4 | 20 | 6 Days | 14 Sep 2026 | 19 Sep 2026 | 20 | 19 Sep 2026 |

Velocity:

Our sprint duration is 6 days and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per iteration unit (story points per day)

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts